## Slide 1
LTFBA update for MESC meeting
3 July 2025

## Slide 2: LTFBA project
Background
The purpose of this project is to facilitate the implementation of the new long-term flow-based allocation (LTFBA) mechanism in line with the requirements defined in the High-Level Market Design (HLMD).
LTFBA will require the long-term transmission rights (LTTRs) for all bidding zone borders in a flow-based capacity calculation region (CCR) to be allocated in a single auction.
Aim
Enhance efficiency and better reflect physical grid constraints.
Expected go-live date
November 2026 for 2027 auctions.

## Slide 3: LTFBA timeline focused on MP involvement
Activity | Aug 25 | Sep 25 | Oct 25 | Nov 25 | Dec 25 | Jan 26 | Feb 26 | Mar 26 | Apr 26 | May 26 | Jun 26 | Jul 26 | Aug 26 | Sep 26 | Oct 26 | Nov 26
Simulation Platform |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
eCAT 8.0 (Cycle 6) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CRDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Website & Publication Tool |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Go Live |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Test w. MPs
SIT* – RCCs, TSOs & MPs
SIT – RCCs, TSOs & MPs
Website SIT – RCCs, TSOs & MPs
Dates TBC: Publication Tool Ext. Parallel Run with MP engagement
Ahead of each activity JAO will formally issue comms to Market Participants with more information regarding their involvement. Dates are to be confirmed but will include timings and details of workshops and alignments, engagement forums and format.
Bid files will be available for MPs on the simulation platform, and output files expected for MPs (e.g. accepted bids and any additional files) - confirmed for 2024 and 2025. Also, there is flexibility to select which order book will be made available to the Market Participants for the simulations.
*SIT: System Integration Testing = overall test of the complete system including the various sub-components. The benefit of aligning the SITs is that JAO and the MPs will see how the developments made as part of the LTFBA project interact as a whole.

## Slide 4
Harmonised Allocation Rules Update
On 27 March 2025, All TSOs submitted to ACER their proposal for the amendment of the harmonized allocation rules (HAR) pursuant to Article 51 of Commission Regulation (EU) 2016/1719 of 26 September 2016.​
ACER has notified that they have commenced the procedure ref. ACER-ELE-2025-003 under Article 5(2)(b) of Regulation (EU) 2019/942 and Articles 4(6)(d), 4(12) and 51 of Regulation (EU) 2016/1719 with a view to decide on this matter within six months, i.e. by 29 September 2025.​
As part of the decision procedure, ACER launched a public consultation on the proposed amendment of the HAR on 24 April 2025 until 22 May 2025. More information on this consultation can be found on ACER’s website.​
Several meetings with ACER, NRAs and TSOs were held between 16 April and 12 June. ACER preliminary position is expected on 20 June.