## Slide 1
MESC meeting – Collateral improvements
8 October 2026

## Slide 2
Collateral Improvements: Indicative roadmap
Go-live no later than end-2028, with the earliest feasible 2028 date targeted subject to procurement outcome and provider commitment.
WORK COMPLETED
INDICATIVE DELIVERY PATH
Q4 2025–Q1 2026
Proof of concept
N-SIDE prototype developed and outcome assessed positively
Q2–Q3 2026
Implementation basis
Functional and technical specifications prepared for competitive vendor selection and integration
Sep–Dec 2026
Procurement
Tender and vendor selection
Jan 2027 onward
Algorithm, Simulation and integration
Implementation
Full rewrite, development, TSO and independent revalidation and testing
From Sep 2027
Auction platform Integration
ORION UI, interfaces and collateral-management integration
Target Q1 2028 onward
End-to-end readiness
Integration testing, TSO/MP testing, operations and deployment
2028
(target Q2 )
Go-live
Earliest feasible date targeted; end-2028 latest commitment
WHY DELIVERY EXTENDS INTO 2028
1
Algorithm redesign
Full rewrite of the LTFBA allocation algorithm
2
Independent assurance
Third-party revalidation plus complete regression and performance testing
3
Multi-platform integration
Simulation and auction platform require coordinated UI and interface changes
4
Market readiness
End-to-end retesting and readiness with TSOs and market participants
Planning dates remain indicative until procurement is concluded and the selected provider confirms the delivery plan.
2