## Regulatory Projects Portfolio
ID | Prioritisation exercise | Project name | Project description | Regulation | Project pipeline | Date of decision | Regulatory deadline | Legal origin of the deadline | Geographical scope | Implementation status | Provisional implementation deadline | On time / delayed | Expected delay [months] | Duration from decision to legal deadline [months] | Realised duration from decision to go-live [months] | Qualitative project priority | Depends on projects | Blocks projects
1 | 2023 | Nordic ID flow-based CC | Introduction of flow-based capacity calculation in the Nordic CCR | CACM | TSOs capacity calculation - Nordic | 2020-10-14 |  | Nordic ID CCM | Regional | To be started | [5 empty] | 0.83333 |  | Flow-based allocation in ID
2 | 2023 | Flow-based allocation in ID (continuous trading) | Introduction of flow-based allocation in SIDC (continuous trading) | CACM | CACM SIDC | 2020-01-30 | 2023-08-01 | Algorithm Methodology | EU | Implementation phase | 2027 | Delayed | 46 | 38 | 84 | 0.33333 | Core ID flow-based CC; Nordic ID flow-based CC
3 | 2024 | Flow-based allocation in ID (IDAs) | Introduction of flow-based allocation in SIDC (intraday auctions) | CACM | CACM SIDC |  |  |  | EU | To be started | [5 empty] | 1
4 | 2024 | Core ID flow-based CC | Implementation of the Core ID CCM pursuant to ACER Decision 03/2024 | CACM | TSOs capacity calculation - Core | 14/03/2024 (ACER Decision 03/2024) | 2026-05-01 | Core ID CCM (2nd and 3rd amendment) | Regional | Implementation phase | 2026-05-01 |  |  |  |  | 0.83333 | Transition to CGMES
5 | 2023 | Core Advanced Hybrid Coupling for DA | Introduction of Advanced Hybrid Coupling (AHC) in the Core region | CACM | CACM SDAC & TSOs capacity calculation - Core | 01/03/2024 (NRAs decision, not ACER) | 2025-06-30 | Core DA CCM (2nd amendment) | Regional | Implementation phase | 2025-06-30 |  |  |  |  | 1
6 | 2023 | Merger of Core & Italy North CCRs for DA | Merger of the two CCRs for DA | CACM | TSOs capacity calculation - Core | 19/03/2024 (ACER Decision 04/2024) |  | Core DA CCM | Regional | To be started |  |  |  | The timing for CCR Central will be proposed on TSOs side when submitting the Central DA CCM to NRAs in 2025 |  | 1.3333
7 | 2023 | Integration of Swiss northern borders in DA CC (Core), enchanced coordination in CC | Agreement needed between Core TSOs and Swissgrid | CACM | TSOs capacity calculation - Core |  |  |  | Regional | Implementation phase | end-2025 |  |  |  |  | 0 | Coordinated validation in Core | Merger of Core & Italy North CCRs for DA
8 | 2023 | Implementation of co-optimisation in SDAC | Pursuant to Article 38 and Article 40 EBGL | CACM | CACM SDAC | 2024-09-01 |  | EB Regulation | EU | Implementation phase (R&D) | [5 empty] | 1
9 | 2024 | Border and NEMO additions in SDAC | Inclusion of new borders and NEMOs in SDAC. This includes, among others: i) integration of EnC contracting parties in SDAC; ii) Celtic interconnector in SDAC. The addition of new borders should be organised in go-live windows which occur within an adequate recurring frequency. | CACM | CACM SDAC |  |  | MCO IP / Core DA CCM | Regional | Continuous task | [5 empty] | Baseload project to be organised in go-live windows
10 | 2024 | Border and NEMO additions in SIDC | Inclusion of new borders and NEMOs in SIDC. This includes, among others: i) integration of EnC contracting parties in SIDC; ii) Celtic interconnector in SIDC. The addition of new borders should be organised in go-live windows which occur within an adequate recurring frequency. | CACM | CACM SIDC |  |  | MCO IP / Core ID CCM | Regional | Continuous task | [5 empty] | Baseload project to be organised in go-live windows
11 | 2024 | ROSC-RDCT Nordic | Introduction of the redispatching, countertrading and cost-sharing methodologies in the Nordic CCR | CACM/SOGL | TSOs capacity calculation - Nordic |  |  | Article 76 SOGL, Article 35 and Article 74 CACM | Regional | To be started | [5 empty] | 0.66667
12 | 2024 | Harmonised market-based implementation Nordic | Implementation of the harmonised market-based implementation by the 'Blueprint TSOs' in the Nordic CCR | EBGL | TSOs capacity calculation - Nordic | 19/07/2023 (ACER Decision 11/2023) | 2026-07-31 | ACER Decision 11/2023 | Regional | Implementation phase | 2026-07-31 |  |  | 24 |  | 1.1667 | Amendment of other methodologies (CIDM, DA CCM, ID CCM, ROSC, BT CCM)
13 | 2024 | Cross-zonal capacity calculation in the balancing timeframe (BTCC) Core | Introduction of the methodology for the calculation of cross-zonal capacity for the balancing timeframe in the Core CCR | EBGL | TSOs capacity calculation - Core | 2023-06-11 |  | Article 37(3) EBGL | Regional | To be started | 2026 |  |  |  |  | 0.5 | Core ID flow-based CC
14 | 2024 | Cross-zonal capacity calculation in the balancing timeframe (BTCC) Nordic | Introduction of the methodology for the calculation of cross-zonal capacity for the balancing timeframe in the Nordic CCR | EBGL | TSOs capacity calculation - Nordic | 2023-08-16 |  | Article 37(3) EBGL | Regional | To be started | [5 empty] | 0.5 | Nordic DA flow-based CC, Nordic ID flow-based CC
15 | 2024 | Coordinated validation in Core | Implementation of the DA coordinated validation process in the Core DA CCM | CACM | TSOs capacity calculation - Core |  | 2025-12-08 | Core DA CCM (3rd amendment) | Regional | Implementation phase | end-2025 |  |  |  |  | 1 |  | Integration of Swiss northern borders in DA CC (Core), enchanced coordination in CC
16 | 2024 | ROSC-RDCT Core | Introduction of the redispatching, countertrading and cost-sharing methodologies in the Core CCR | CACM/SOGL | TSOs capacity calculation - Core | 30 November 2020 (ACER Decision 30/2020) and 4 December 2020 (ACER Decision 33/2020 and ACER Decision 35/2020) | i) 04/06/2023; ii) 04/06/2025 | Article 76 SOGL, Article 35 and Article 74 CACM | Regional | Implementation phase | i) Q4 2026 - Q4 2028 | Delayed | 42-66 |  |  | 1 | Transition to CGMES
17 | 2024 | ID gate closure time no more than 30 min before real-time | Shortening of the IDGCT as foreseen by the EMD reform. TSOs may request derogations until mid-2031 | CACM | CACM SIDC |  | 2026-01-01 | EMD reform | EU | To be started | [5 empty] | 1.3333

## Prioritisation
ID | Prioritisation exercise | Project name | Regulation | Project pipeline | Qualitative project priority | 1. Overall efficiency | 1a. Overall benefits compared to costs for all stakeholders and impact on assets and implementation efforts 1b. Market consensus | 2. Effectiveness to enhance market integration | 2a. Allows the extension to new bidding zones/bidding zone borders 2b. Allows for harmonisation of rules or processes (either across timeframes/regions) 2c. Coherence with principles/functioning of the EU policies in general (such as decarbonisation, SoS, etc.) and other timeframes/regions/markets | 3. Effectiveness to ensure non-discrimination | 3a. Allows to treat all players equally, if the circumstances are equal 3b. Removes discriminating rule | 4. Effectiveness to increase competition | 4a. Allows for competition between new borders/bids of market participants 4b. Removes entry/exit barriers | 5. Effectiveness to enhance the efficient functioning of the market | 5a. Improves price signals 5b. Improves welfare 5c. Improves operational stability
1 | 2023 | Nordic ID flow-based CC | CACM | TSOs capacity calculation - Nordic | 0.83333 | 0 | + High potential benefits - Complex implementation | 2 | + Allows for the harmonisation of the capacity constraints across the different timeframes | 1 | + Removes discrimination between internal and cross-border exchanges | 1 | + Allows for additional competition between the borders | 1 | + Improves operational stability
2 | 2023 | Flow-based allocation in ID (continuous trading) | CACM | CACM SIDC | 0.33333 | -1 | + Potential benefits - Complex implementation | 1 | + Allows for the harmonisation of the capacity constraints | 0 | Neutral | 1 | + Allows for competition between the borders | 2 | + Likely added social welfare and improved price signals due to optimised capacity allocation
3 | 2024 | Flow-based allocation in ID (IDAs) | CACM | CACM SIDC | 1 | 1 | + Potential benefits + Simple implementation | 1 | + Allows for the harmonisation of the capacity constraints | 0 | Neutral | 1 | + Allows for competition between the borders | 2 | + Likely added social welfare and improved price signals due to optimised capacity allocation
4 | 2024 | Core ID flow-based CC | CACM | TSOs capacity calculation - Core | 0.83333 | 0 | + High potential benefits - Complex implementation | 2 | + Allows for the harmonisation of the capacity constraints across the different timeframes | 1 | + Removes discrimination between internal and cross-border exchanges | 1 | + Allows more bids to compete for the available cross-zonal capacity | 1 | + Improves operational stability
5 | 2023 | Core Advanced Hybrid Coupling for DA | CACM | CACM SDAC & TSOs capacity calculation - Core | 1 | 1 | + Potential benefits + Simple implementation | 1 | + Allows for harmonisation between Nordic and Core CCRs | 1 | + Removes discrimination between extra-regional and intra-regional exchanges | 1 | + Allows for flow-based benefits for DC cables | 1 | + Improves operational stability
6 | 2023 | Merger of Core & Italy North CCRs for DA | CACM | TSOs capacity calculation - Core | 1.3333 | 1 | + High potential benefits - Moderate implementation | 2 | + Allows for harmonisation between Core and ITN rules | 1 | + Removes discrimination between internal and cross-border exchanges for the ITN region | 2 | + Allows for additional competition between the borders and expanding regions | 1 | + Improves operational stability
7 | 2023 | Integration of Swiss northern borders in DA CC (Core), enchanced coordination in CC | CACM | TSOs capacity calculation - Core | 0 | -1 | + Low potential benefits - Complex implementation | 1 | + Integration of Swiss borders | 0 | Neutral | 0 | Neutral | 1 | + Improves operational stability
8 | 2023 | Implementation of co-optimisation in SDAC | CACM | CACM SDAC | 1 | -1 | + Very high potential benefits - Extremely complex implementation | 2 | + Allows for the integration of balancing capacity markets (key requirement) | 2 | + Allows for market participants that do not have the requirements to trade on the DA market to access cross-border capacity, all DA market participants can participate in balancing capacity markets | 2 | + Opens competition between two key market segments (DA and balancing capacity, key requirement) | 2 | + Likely added social welfare and improved price signals due to optimised capacity allocation
9 | 2024 | Border and NEMO additions in SDAC | CACM | CACM SDAC | Baseload project to be organised in go-live windows
10 | 2024 | Border and NEMO additions in SIDC | CACM | CACM SIDC | Baseload project to be organised in go-live windows
11 | 2024 | ROSC-RDCT Nordic | CACM/SOGL | TSOs capacity calculation - Nordic | 0.66667 | 1 | + High potential benefits - Moderate implementation | 1 | + Improved congestion management | 0 | Neutral | 0 | Neutral | 1 | + Improves operational stability
12 | 2024 | Harmonised market-based implementation Nordic | EBGL | TSOs capacity calculation - Nordic | 1.1667 | 1 | + Very high potential benefits - Complex implementation | 2 | + Allows for an harmonised approach and for the integration of balancing capacity markets | 0 | Neutral | 1 | + Competition between BSPs | 2 | + Likely added social welfare and improved price signals due to optimised capacity allocation, and allows other regions to follow
13 | 2024 | Cross-zonal capacity calculation in the balancing timeframe (BTCC) Core | EBGL | TSOs capacity calculation - Core | 0.5 | 0 | + High potential benefits - Complex implementation | 1 | + Consistency with capacity calculation in other timeframes | 0 | Neutral | 1 | + Increased competition | 1 | + Improves operational stability
14 | 2024 | Cross-zonal capacity calculation in the balancing timeframe (BTCC) Nordic | EBGL | TSOs capacity calculation - Nordic | 0.5 | 0 | + High potential benefits - Complex implementation | 1 | + Consistency with capacity calculation in other timeframes | 0 | Neutral | 1 | + Increased competition | 1 | + Improves operational stability
15 | 2024 | Coordinated validation in Core | CACM | TSOs capacity calculation - Core | 1 | 1 | + High potential benefits - Moderate implementation | 1 | + Harmonisation of processes in the DA timeframe | 1 | + Allows more cross-zonal capacity to be made available in DA | 1 | + More cross-border competition in DA | 1 | + Improves operational stability
16 | 2024 | ROSC-RDCT Core | CACM/SOGL | TSOs capacity calculation - Core | 1 | 1 | + Very high potential benefits - Complex implementation | 2 | + Improved congestion management and harmonisation of processes across the region | 1 | + Triggers expiration of 70% derogations in the Core region | 0 | Neutral | 1 | + Improves operational stability
17 | 2024 | ID gate closure time no more than 30 min before real-time | CACM | CACM SIDC | 1.3333 | 1 | + Potential benefits + Simple implementation | 2 | + Improved congestion management and improved liquidity in ID market | 0 | Neutral | 2 | + Opens competition to new bids and allow new MPs into SIDC | 2 | + Likely added social welfare and improved price signals in SIDC
18 | 2023 | Pan-EU IDAs | CACM | CACM SIDC | 1.1667 | 0 | + High potential benefits - Complex implementation | 2 | + Allows for competition between the borders and brings the ID market closer to the DA design | 1 | + Auctions are naturally less discriminatory than continuous | 2 | + Allows market participants to join SIDC without continuous ID trading | 2 | + Prices ID capacity (key requirement)
19 | 2023 | Nordic DA flow-based CC | CACM | TSOs capacity calculation - Nordic | 1 | 1 | + Very high potential benefits - Complex implementation | 1 | + Allows for more harmonisation between CCRs on CC | 1 | + Removes discrimination between internal and cross-border exchanges | 1 | + Allows for additional competition between the borders | 1 | + Improves operational stability
20 | 2023 | Nordic DA flow-based CA | CACM | CACM SDAC | 1.3333 | 2 | + High potential benefits + Simple implementation | 1 | + Allows for more harmonisation between CCRs on CC | 0 | Neutral | 1 | + Allows for additional competition between the borders | 2 | + Likely added social welfare and improved price signals due to optimised capacity allocation
21 | 2023 | Core ID flow-based CC (2019) | CACM | TSOs capacity calculation - Core | 0.83333 | 0 | + High potential benefits - Complex implementation | 2 | + Allows for the harmonisation of the capacity constraints across the different timeframes | 1 | + Removes discrimination between internal and cross-border exchanges | 1 | + Allows for additional competition between the borders | 1 | + Improves operational stability
22 | 2023 | 15' MTU implementation ID | CACM | CACM SIDC | 0.83333 | 0 | + High potential benefits - Complex implementation | 1 | + Brings SIDC closer to a common MTU for all timeframes | 1 | + Allows specific MPs (e.g. solar generators) to bid | 1 | + Removes entry barrier for market participants needing a 15' product granularity | 2 | + Likely added social welfare and improved price signals due to increased time granularity
23 | 2023 | 15' MTU implementation DA | CACM | CACM SDAC | 0 | -2 | + Low potential benefits - Very complex implementation | 1 | + Brings SDAC closer to a common MTU for all timeframes | 0 | + Could allow specific MPs (e.g. solar generators) to bid - Could force MPs to bid with a 15' granularity | 1 | + Removes entry barrier for market participants needing a 15' product granularity | 2 | + Likely added social welfare and improved price signals due to increased time granularity

## Regulatory Projects Pipelines
Project pipeline | Number of projects in paralllel
CACM SDAC | 3
CACM SIDC | 4
TSOs capacity calculation - Core | 7
TSOs capacity calculation - Nordic | 4

## Full list of projects
ID | Project name | Project description | Regulation | Project pipeline | Date of decision | Regulatory deadline | Legal origin of the deadline | Geographical scope | Implementation status | Provisional implementation deadline | On time / delayed | Expected delay [months] | Duration from decision to legal deadline [months] | Realised duration from decision to go-live [months] | Qualitative project priority | Depends on projects | Blocks projects | Comments
2 | Flow-based allocation in ID (continuous trading) | Introduction of flow-based allocation in SIDC (continuous trading) | CACM | CACM SIDC | 2020-01-30 | 2023-08-01 | Algorithm Methodology | EU | Implementation phase | 2027 | Delayed | 46 | 38 | 84 | 0.33333 | Core ID flow-based CC; Nordic ID flow-based CC
5 | Core Advanced Hybrid Coupling for DA | Introduction of Advanced Hybrid Coupling (AHC) in the Core region | CACM | CACM SDAC & TSOs capacity calculation - Core | 01/03/2024 (NRAs decision, not ACER) | 2025-06-30 | Core DA CCM (2nd amendment) | Regional | Implementation phase | 2025-06-30 |  |  |  |  | 1
6 | Merger of Core & Italy North CCRs for DA | Merger of the two CCRs for DA | CACM | TSOs capacity calculation - Core | 19/03/2024 (ACER Decision 04/2024) |  | Core DA CCM | Regional | To be started |  |  |  | The timing for CCR Central will be proposed on TSOs side when submitting the Central DA CCM to NRAs in 2025 |  | 1.3333
7 | Integration of Swiss northern borders in DA CC (Core), enchanced coordination in CC | Agreement needed between Core TSOs and Swissgrid | CACM | TSOs capacity calculation - Core |  |  |  | Regional | Implementation phase | end-2025 |  |  |  |  | 0 | Coordinated validation in Core
1 | Nordic ID flow-based CC | Introduction of flow-based capacity calculation in the Nordic CCR | CACM | TSOs capacity calculation - Nordic |  |  | Nordic ID CCM | Regional | To be started | [5 empty] | 0.83333 |  | Flow-based allocation in ID
| Long-term flow-based allocation |  | FCA | All application TSOs |  |  |  | Regional | To be started | [6 empty] | Long-term flow-based CC Core; Long-term flow-based CC Nordic
| Long-term flow-based CC Nordic |  | FCA | TSOs capacity calculation - Nordic | 30/10/2019 (ACER Decision 16/2019) | 12 months after DA Nordic CCM | Nordic LT CCM | Regional |  | 2025-10-01 | [6 empty] | Long-term flow-based allocation
11 | ROSC-RDCT Nordic | Introduction of the redispatching, countertrading and cost-sharing methodologies in the Nordic CCR | CACM/SOGL | TSOs capacity calculation - Nordic |  |  | Article 76 SOGL, Article 35 and Article 74 CACM | Regional | [6 empty] | 0.66667
16 | ROSC-RDCT Core | Introduction of the redispatching, countertrading and cost-sharing methodologies in the Core CCR | CACM/SOGL | TSOs capacity calculation - Core | 30 November 2020 (ACER Decision 30/2020) and 4 December 2020 (ACER Decision 33/2020 and ACER Decision 35/2020) | i) 04/06/2023; ii) 04/06/2025 | Article 76 SOGL, Article 35 and Article 74 CACM | Regional | Implementation phase | i) Q4 2026 - Q4 2028 | Delayed | 42-66 |  |  | 1 | Transition to CGMES
| ROSC-RDCT SEE |  | CACM/SOGL | TSOs capacity calculation - SEE | 4 December 2020 (ACER Decision 34/2020) |  | Article 76 SOGL, Article 35 and Article 74 CACM | Regional |  | 2025-06-04
| Nordic mFRR balancing capacity market |  | EBGL | TSOs capacity calculation - Nordic |  |  | ACER Decision 21/2020 and ACER Decision 22/2020, Nordic NRAs decision pending | Regional | To be started
| Baltic market based implementation |  | EBGL | TSOs capacity calculation - Baltic | 2021-08-13 | Linked to Baltic CACM CCM go-live | ACER Decision 10/2021 | Regional |  | On the day of synchronisation | On time |  | Approximately 3.5 years |  |  | Synchronisation and amendment of other methodologies (CIDM, DA CCM, ID CCM, ROSC, BT CCM)
8 | Implementation of co-optimisation in SDAC | Pursuant to Article 38 and Article 40 EBGL | CACM | CACM SDAC | 2024-09-01 |  | EB Regulation | EU | Implementation phase (R&D) | [5 empty] | 1
| Common grid model methodology |  | FCA | All TSOs | 2018-06-11 | 2019-07-11 | FCA Regulation Article 18 | EU | Implementation phase
| Long-term flow-based CC Core |  | FCA | TSOs capacity calculation - Core | 18 January 2023 (ACER Decision 03/2023) | 2025-01-01 | Core LT CCM | Regional | Implementation phase | 2025-11-01 | On time |  | 22 |  |  |  | Long-term flow-based allocation | It will be implemented in UCTE format. The move to CGMES is expected to be completed by Q4 2027.
| Long-term CC Baltic |  | FCA | TSOs capacity calculation - Baltic
| Bidding zone review Nordics |  | CACM | TSOs capacity calculation - Nordic |  | 2023-08-08 | Electricity Regulation | EU | Implementation phase |  | Delayed |  | 19
| Bidding zone review Core |  | CACM | TSOs capacity calculation - Core |  | 2023-08-08 | Electricity Regulation | EU | Implementation phase |  | Delayed |  | 28
| PICASSO aFRR implementation - TSO accession |  | EBGL | Balancing | 2020-01-24 | 2024-07-01 | EB Regulation | EU | Implementation phase
| MARI mFRR implementation - TSO accession |  | EBGL | Balancing | 2020-01-24 | 2024-07-01 | EB Regulation | EU | Implementation phase
21 | Core ID flow-based CC (2019) |  | CACM | TSOs capacity calculation - Core | 2019-02-01 |  | Core ID CCM | Regional | Implementation phase | 2024-06-01 | [6 empty] | Flow-based allocation in ID
18 | Pan-EU IDAs |  | CACM | CACM SIDC | 2020-01-30 | 2023-01-01 | Algorithm Methodology | EU | Implementation phase | 2024-06-13 | Delayed | 17 | 35
| Nordic flow-based DA CC |  | CACM | TSOs capacity calculation - Nordic | 2019-12-01 |  | Nordic DA CCM | Regional | Implementation phase | 2024-10-01 | Delayed | [5 empty] | Nordic flow-based DA CA
| Nordic flow-based DA CA |  | CACM | CACM SDAC | 2018-07-10 |  | Nordic DA CCM | Regional | Implementation phase | 2024-10-01 | Delayed |  |  |  |  | Nordic flow-based DA CC
23 | 15' MTU implementation DA |  | CACM | CACM SDAC | 2019-06-05 | 2021-01-01 | Electricity Regulation | EU | Implementation phase | 2025-01-01 | Delayed | 48 | 18 |  |  | PUN phase-out and scalable complex orders
9 | Border and NEMO additions in SDAC | Inclusion of new borders and NEMOs in SDAC. This includes, among others: i) integration of EnC contracting parties in SDAC; ii) Celtic interconnector in SDAC. The addition of new borders should be organised in go-live windows which occur within an adequate recurring frequency. | CACM | CACM SDAC |  |  | MCO IP / Core DA CCM | Regional | Continuous task | [5 empty] | Baseload project to be organised in go-live windows
10 | Border and NEMO additions in SIDC | Inclusion of new borders and NEMOs in SIDC. This includes, among others: i) integration of EnC contracting parties in SIDC; ii) Celtic interconnector in SIDC. The addition of new borders should be organised in go-live windows which occur within an adequate recurring frequency. | CACM | CACM SIDC |  |  | MCO IP / Core ID CCM | Regional | Continuous task | [5 empty] | Baseload project to be organised in go-live windows
3 | Flow-based allocation in ID (IDAs) | Introduction of flow-based allocation in SIDC (intraday auctions) | CACM | CACM SIDC |  |  |  | EU | To be started | [5 empty] | 1
4 | Core ID flow-based CC | Implementation of the Core ID CCM pursuant to ACER Decision 03/2024 | CACM | TSOs capacity calculation - Core | 14/03/2024 (ACER Decision 03/2024) | 2026-05-01 | Core ID CCM (2nd and 3rd amendment) | Regional | Implementation phase | 2026-05-01 |  |  |  |  | 0.83333 | Transition to CGMES
13 | Cross-zonal capacity calculation in the balancing timeframe (BTCC) Core | Introduction of the methodology for the calculation of cross-zonal capacity for the balancing timeframe in the Core CCR | EBGL | TSOs capacity calculation - Core | 2023-06-11 |  | Article 37(3) EBGL | Regional | To be started | 2026 |  |  |  |  | 0.5 | Core ID flow-based CC
14 | Cross-zonal capacity calculation in the balancing timeframe (BTCC) Nordic | Introduction of the methodology for the calculation of cross-zonal capacity for the balancing timeframe in the Nordic CCR | EBGL | TSOs capacity calculation - Nordic | 2023-08-16 |  | Article 37(3) EBGL | Regional | To be started | [5 empty] | 0.5 | Nordic DA flow-based CC, Nordic ID flow-based CC
| Cross-zonal capacity calculation in the balancing timeframe (BTCC) Italy North |  | EBGL | TSOs capacity calculation - Italy North | 2023-11-24 | 12 months after ROSC | Article 37(3) EBGL | Regional | To be started
| Cross-zonal capacity calculation in the balancing timeframe (BTCC) SWE |  | EBGL | TSOs capacity calculation - SWE | 2023-06-01 |  | Article 37(3) EBGL | Regional | To be started
| Cross-zonal capacity calculation in the balancing timeframe (BTCC) SEE |  | EBGL | TSOs capacity calculation - SEE | 2024-01-23 | 12 months after ROSC v2 | Article 37(3) EBGL | Regional | To be started
| Cross-zonal capacity calculation in the balancing timeframe (BTCC) Hansa |  | EBGL | TSOs capacity calculation - Hansa |  |  | Article 37(3) EBGL | Regional | To be started
| Cross-zonal capacity calculation in the balancing timeframe (BTCC) Greece-Italy |  | EBGL | TSOs capacity calculation - Greece-Italy | 2023-06-27 |  | Article 37(3) EBGL | Regional | To be started
| Cross-zonal capacity calculation in the balancing timeframe (BTCC) Baltic |  | EBGL | TSOs capacity calculation - Baltic |  |  | Article 37(3) EBGL | Regional | To be started
15 | Coordinated validation in Core | Implementation of the DA coordinated validation process in the Core DA CCM | CACM | TSOs capacity calculation - Core |  | 2025-12-08 | Core DA CCM (3rd amendment) | Regional | Implementation phase | end-2025 |  |  |  |  | 1 |  | Integration of Swiss northern borders in DA CC (Core), enchanced coordination in CC
22 | 15' MTU implementation ID |  | CACM | CACM SIDC |  | 2021-01-01 | Electricity Regulation | EU | Implementation phase | 2025-01-01 | Delayed | 48 | 18 |  |  |  | 15' MTU implementation DA
| Harmonised market-based implementation Core | Reserving cross-zonal capacity for the exchange of balancing capacity | EBGL | TSOs capacity calculation - Core | 19/07/2023 (ACER Decision 11/2023) |  | ACER Decision 11/2023 | Regional | To be started | [6 empty] | Amendment of other methodologies (CIDM, DA CCM, ID CCM, ROSC, BT CCM)
12 | Harmonised market-based implementation Nordic | Implementation of the harmonised market-based implementation by the 'Blueprint TSOs' in the Nordic CCR | EBGL | TSOs capacity calculation - Nordic | 19/07/2023 (ACER Decision 11/2023) | 2026-07-31 | ACER Decision 11/2023 | Regional | Implementation phase | 2026-07-31 |  |  | 24 |  | 1.1667 | Amendment of other methodologies (CIDM, DA CCM, ID CCM, ROSC, BT CCM)
| Harmonised market-based implementation Baltic |  | EBGL | TSOs capacity calculation - Baltic | 19/07/2023 (ACER Decision 11/2023) |  | ACER Decision 11/2023 | Regional | Implementation phase | [6 empty] | Amendment of other methodologies (CIDM, DA CCM, ID CCM, ROSC, BT CCM)
| Transition to CGMES |  | CACM, SOGL, FCA | TSOs capacity calculation - Core |  |  |  | Regional | Implementation phase | Q4 2027 | [6 empty] | ROSC-RDCT Core, Core ID flow-based CC
17 | ID gate closure time no more than 30 min before real-time |  | CACM | CACM SIDC |  | 2026-01-01 | EMD reform | EU | To be started | [5 empty] | 1.3333
| FTR options allocation in Y-2 and Y-3 |  | FCA | All TSOs |  |  |  |  | To be started
| Non-uniform pricing |  | CACM | CACM SDAC |  |  |  | EU | To be started
| MRLVC with UK |  | CACM | CACM SDAC |  | 2022 | EU-UK TCA | Regional | On hold