## Slide 1: Bidding zones Review indicative timeline (by May 2024)
BZR started
Final common report and output data publication
(Dec 2024)
Modelling and Calculations for CE BZRR
PAN EU studies on common indicators
Public webinar
Aug 22
Consultative group meeting
Step 2: Assessment of all other criteria
Step 3: Reject configur
Step 4: Consolidat results
Step 1: monetised benefits
Modelling and Calculations for Nordic BZRR
Public consultation
(4 - 6 weeks)
Consultative group meeting
Public webinar
Consultative group meeting
Final PAN EU studies (liquidity study and transition costs study)
(Oct 2024)
Add 2 config. CE
(Aug-Sep 2024)
Final common report and approval
KEY Messages:
Final delivery of the BZ review – common for both regions – Dec 2024
If there are delays in one Region the process may be split
Very tight timeline. No contingency. High commitment from the TSOs.
Steps as defined in the methodology
Main deliverables
Stakeholders interaction
May 24
Jun 24
Jul 24
Aug 24
Sep 24
Oct 24
Nov 24
Dec 24
Regional webinar: Nordics…