## Slide 1: The Electricity Integration Package in the Energy Community - Update
Jasmina Trhulj, Energy Community Secretariat
37th MESC, 8 October 2024

## Slide 2
The Electricity Integration Package obligations and minimum requirements for EnC CPs adherence to SDAC and SIDC
        Transposition of the Electricity Integration Package (EIP)
          Deadline: 31 December 2023
        The MCO Integration Plan submission
          by all EU and EnC NEMOs to all EU and EnC NRAs, ECRB and ACER
          Deadline: 15 December 2023
          It was timely drafted by all EU NEMOs but its official submission was postponed to 15 June, due to the delayed transposition and consequently a lack of compliantly designated NEMOs in any of the Contracting Parties (upon recommendation of EC, ECS and ACER)
        EnC CCRs operationalisation
          All TSOs of Shadow SEE CCR and EE CCR to sign a cooperation agreement
          All TSOs of EnC CCRs to submit a common coordinated capacity calculation methodology for DA and ID
          Deadline: 15 June 2023

## Slide 3
EC and EnCS letter as of 13 June 2024
Imminent steps by no later than 15 October 2024
        As no progress has been made, on 13 June 2024 the European Commission and the Energy Community Secretariat sent a letter to the Contracting Parties’ ministers urging:
        CPs to complete the transposition of the EIP and valid designation of at least one NEMO
        NEMOs to submit the MCO Integration Plan by 15 October 2024
        TSOs to operationalize EnC CCRs
          All EU TSOs, in consultation with Energy Community TSOs, should submit an amendment to the pan-EU CCR determination pursuant to Article 15 of Regulation (EU) 2015/1222 to ACER that will include all bidding zone borders of the three EnC CCRs.
          For each EnC CCR, the following implementation steps are to be taken:
            cooperation agreements are signed among all involved TSOs of Contracting Parties and Member States;
            regional TCMs submitted to the respective NRAs for approval
            governance structures for the required processes on NRA level are established.
        TSOs and NEMOs of each LIP to define a roadmap

## Slide 4
4
The Electricity Integration Package - Transposition Status
Drafts currently aligned with the entities’ ministries
Not yet submitted to ECS for review
First draft developed by EnCS with EU4Energy support and submitted to the Ministry in September 2024
Public consultation concluded on 23 Sep
EnCS reviewed draft Electriicty Law and secondary acts transposing NC&GL
Public consultation concluded on 11 Sep
ECS reviewed the draft Energy Law
NEMO-related articles still in drafting
New draft version delivered to the Ministry on 23 July by ESP, supported by EnCS
Ministry is currently finalizing the draft with UA stakeholders
First draft expected to be submitted to EnCS in October 2024
New Government resumed the drafting
New draft to be submitted to ECS soon
Public consultation of the Energy Law concluded in September 24, reviewed by ECS
The Law on XB to be publicly consulted in October 24
Ukraine
Georgia
Moldova
Albania
North Macedonia
Montenegro
Serbia
Bosnia and Herzegovina
ECS reviewed draft Laws on Energy and Electricity in March 2024
New draft versions expected in October 2024
Kosovo*
        The EnC Secretariat started an infringement case against all CPs for non-transposition of the Electricity Integration Package
        PHLG meeting on 11 December and the Ministerial Council on 12 December
Notes: The main precondition for market coupling is the transposition of the Electricity Integration Package. The deadline of Dec 2023 was missed by all Contracting Parties and until now further delays are expected.
Several CPs have submitted draft primary legislation for the Secretariat’s review, partly developed with the support of technical assistance conducted by e.g EU4E, Secretariat or other donors.
Nevertheless, the transposition is currently too slow to keep up with the required pace and after the MC urged the completion of the transposition in the first quarter of 2024, the Secretariat is about to launch infringement procedures against all Contracting Parties for non-transposition.

## Slide 5
5
EnC CPs’ NEMO status and MCO IP submission
No DA/ID market
DA/ID live
No interconnections with EU MS and EnC CPs
Monopoly status notified
No DA/ID market
Monopoly status notified
DA and ID live
NEMO: SEEPEX
Monopoly status notified
DA and ID live (JSC MO)
AL+XK*: DA live & coupled
NEMO: ALPEX
AL+XK*: ID live &coupling in November 24
Monopoly status notified
DA live
NEMO: MEMO
Monopoly status notified
DA live
NEMO: MEPX
Ukraine
Georgia
Moldova
Albania
Kosovo*
North Macedonia
Montenegro
Serbia
Bosnia and Herzegovina
        The Secretariat publishes a list reflecting information on NEMO designation status as notified by the Contracting Parties.
        EnC JET meeting as of 11 September 2023: EC recommends not to delay further the MCO IP submission, EnC NEMOs to be included in the finalisation process on informal basis. EU NEMOs have asked EC to provide the statement also in written. The written statement shall include exact deadline when the MCO IP shall be submitted.
        Currently designated NEMOs are not considered as compliantly designated NEMOs because they are designated before the Electricity Integration Package is transposed.

## Slide 6
EnC CCRs | Cooperation Agreement signed | Capacity calculation methodology adopted | LIP established
ITME CCR | Cooperation established, no obligation for an agreement | NO Drafted by TSOs and submitted to the NRAs for approval | ITME LIP applied for IBWT
EE CCR | NO Drafting and the negotiation on the cost sharing key completed on 11 September 2024, removing the remaining obstacle to its finalization and signature. | NO Interim methodology drafted and agreed by TSOs, to be approved by NRAs | EE LIP MoU finalized, scheduled to be signed in the first week of October 2024
Shadow SEE CCR | NO The operationalisation has not started yet due to negotiations on possible reconfiguration facilitated by ENTSO-E. The discussion on the proposal and its practical implementation is to be continued in the high-level meeting on 2 October 2024. | NO | HU-RS LIP, MoU signed SEE MC LIP (AL, GR, XK*, MK), MoU signed, applied for IBWT
EnC CCRs and LIPs - update

## Slide 7
jasmina.trhulj@energy-community.org
Thank you for your attention!