## READ ME
Purpose of this document is to provide visibility of the efforts made, locally at data providers as well as centrally at ENTSO-E, to implement the provisions of the MoP.
For regulation articles that do not have a corresponding tab, the ENTSO-E transparency platform and all data providers by default comply with the most latest version of the MoP.
This edition of the MoP implementation roadmap covers all evolution up until and including MoP v3r5.

## TR 10.1.a
Regulation article | Publication name
TR 10.1.a | planned unavailability in transmission grid
Evolution: | MoP v3r5: Two additional publication modes (available/installed capacity or unavailable import/export capability per BZ)
country/area | TSO | status as of today | target date MoP v3r5 implementation | notes
transparency platform | ENTSO-E | v3r4 | Q4 2025
Albania | OST
Austria | APG | v3r4 | Q4 2026 | Switch to new publication mode (Installed/Avaialble capacity) planned.
Belgium | ELIA | v3r4 | Q2 2026
Bosnia and Herzegovina | NOSBIH
Bulgaria | ESO | v3r3 | Q1 2026 | will be updated under MoP v3r5 (xsd v 4:2)
Croatia | HOPS |  | Q3 till Q4 2026
Czechia | CEPS | v3r3 | Q1 2026 | will be updated under MoP v3r5 (xsd v 4:2)
France | RTE | v3r4 | Q4 2026
Georgia | GSE
Germany | 50Hertz | v3r4 | Q4 2025 till Q1 2026 | Switch to new publication mode (Installed/Avaialble capacity) planned.
Germany | AMPRION | v3r4
Germany | TENNETDE | v3r4 | Q4 2025 till Q1 2026 | Switch to new publication mode (Installed/Available capacity) planned.
Germany | TRANSNETBW | v3r4 | Q4 2025 till Q1 2026 | Switch to new publication mode (Installed/Avaialble capacity) planned.
Great Britain | BRITNED
Great Britain (ElecLink) | ElecLink
Greece | ADMIE
Hungary | MAVIR | v3r4 | Q3 2026 | Switch to new publication mode (Installed/Avaialble capacity) planned.
Ireland | EIRGRID
Italy | TERNA | v3r4 | Q4 2025 / Q1 2026 | Switch to new publication mode (Installed/Avaialble capacity) planned.
Kosovo | KOSTT
Latvia | AST | v3r4 | NTC-based capacity allocation. | No changes are expected with 3.5
Lithuania | LITGRID
Luxembourg | CREOS
Montenegro | CGES
Netherlands | TENNETNL | v3r4
North Macedonia | MEPSO
Northern Ireland | SONI
Norway | STATNETT |  |  | N/A
Poland | PSE | v3r4 | Implementation date to be determined.
Portugal | REN
Romania | TEL | v3r3 | Q42026 | will be updated according to MoP v3r5 and xsd v 4:2
Serbia | EMS
Slovakia | SEPS
Slovenia | ELES
Spain | REE | v3r4 | NTC-based capacity allocation | No changes are expected with 3.5
Switzerland | SWISSGRID | v3r4 | Undefined | Need clarification concerning harmonization of the impact on interconnection capacity for Flow-based vs NTC based allocation methods
Ukraine | UKRENERGO
Multiple BZN and/or CTA | RNP
Multiple BZN and/or CTA | NORDPOOL
Multiple BZN and/or CTA | NUCS | v3r3 | Q1 2026

## TR 10.1.b
Regulation article | Publication name
TR 10.1.a | unplanned unavailability in transmission grid
Evolution: | MoP v3r5: Two additional publication modes (available/installed capacity or unavailable import/export capability per BZ)
country/area | TSO | status as of today | target date MoP v3r5 implementation | notes
transparency platform | ENTSO-E | v3r4 | Q4 2025
Albania | OST
Austria | APG | v3r4 | Q4 2026 | Switch to new publication mode (Installed/Avaialble capacity) planned.
Belgium | ELIA | v3r4 | Q2 2026
Bosnia and Herzegovina | NOSBIH
Bulgaria | ESO | v3r3 | Q1 2026 | will be updated under MoP v3r5 (xsd v 4:2)
Croatia | HOPS |  | Q3 till Q4 2026
Czechia | CEPS | v3r4 | Q1 2026
France | RTE | v3r4 | Q4 2026
Georgia | GSE
Germany | 50Hertz | v3r4 | Q4 2025 till Q1 2026 | Switch to new publication mode (Installed/Avaialble capacity) planned.
Germany | AMPRION | v3r4
Germany | TENNETDE | v3r4 | Q4 2025 till Q1 2026 | Switch to new publication mode (Installed/Avaialble capacity) planned.
Germany | TRANSNETBW | v3r4 | Q4 2025 till Q1 2026 | Switch to new publication mode (Installed/Avaialble capacity) planned.
Germany | 50Hertz
Great Britain | BRITNED
Great Britain | ElecLink
Great Britain - Denmark | RNP
Greece | ADMIE
Hungary | MAVIR | v3r4 | Q3 2026 | Switch to new publication mode (Installed/Avaialble capacity) planned.
Ireland | EIRGRID
Italy | TERNA | v3r4 | Q4 2025 / Q1 2026 | Switch to new publication mode (Installed/Avaialble capacity) planned.
Kosovo | KOSTT
Latvia | AST | v3r4 | NTC-based capacity allocation | No changes are expected with 3.5
Lithuania | LITGRID
Luxembourg | CREOS
Montenegro | CGES
Netherlands | TENNETNL | v3r4
North Macedonia | MEPSO
Northern Ireland | SONI
Norway | STATNETT |  |  | N/A
Poland | PSE | v3r4 | Implementation date to be determined.
Portugal | REN
Romania | TEL | v3r3 | Q4 2026 | will be updated according to MoP v3r5 and xsd v 4:2
Serbia | EMS
Slovakia | SEPS
Slovenia | ELES
Spain | REE | v3r4 | NTC-based capacity allocation | No changes are expected with 3.5
Sweden | SVK | v3r4
Switzerland | SWISSGRID | v3r4 | Undefined | Need clarification concerning harmonization of the impact on interconnection capacity for Flow-based vs NTC based allocation methods
Ukraine | UKRENERGO
Multiple BZN and/or CTA | NORDPOOL
Multiple BZN and/or CTA | NUCS | v3r3 | Q1 2026

## TR 11.1.a NTC forecasts
Regulation article | Publication name
TR 11.1.a | forecast capacity
Evolution: | MoP v3r4: Negative values permitted
country/area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r4
Albania | OST
Austria | APG | v3r4 | In practice negative values do not exist in our case
Belgium | ELIA | v3r4 | In practice negative values do not exist in our case
Bosnia and Herzegovina | NOSBIH
Bulgaria | ESO | v3r4 | In practice negative values do not exist in our case
Croatia | HOPS |  | In practice negative values do not exist in our case
Czechia | CEPS | v3r4
Estonia | ELERING
France | RTE | v3r4 | In practice negative values do not exist in our case.
Georgia | GSE
Germany | 50Hertz | v3r4
Germany | TENNETDE | v3r4 | In practice negative values do not exist in our case. We are using doc version 7:0. Later versions of MoP require version 7:3
Great Britain | BRITNED
Great Britain | ElecLink
Great Britain | RNP
Greece | ADMIE
Hungary | MAVIR | v3r4 | No changes detected compared to v3r4 content
Ireland | EIRGRID
Italy | Coreso
Italy | TERNA | v3r4
Kosovo | KOSTT
Latvia | AST | v3r4
Lithuania | LITGRID
Luxembourg | CREOS
Montenegro | CGES
Netherlands | TENNETNL | v3r4
North Macedonia | MEPSO
Northern Ireland | SONI
Poland | PSE
Portugal | REN
Romania | TEL | v3r3 | In practice negative values do not exist in our case. We are using doc version 7:0. Later versions of MoP require version 7:3
Serbia | EMS
Slovakia | SEPS
Spain | REE | v3r4 | NTC-based capacity allocation
Switzerland | SWISSGRID | v3r4 | In practice negative values do not exist in our case.
Ukraine | UKRENERGO
Multiple | NORDPOOL
Multiple | NUCS | v3r3

## TR 11.1.b
Regulation article | Publication name
TR 11.1.b | flow-based allocations
Evolution: | MoP v3r4: Deanonymisation and additional parameters MoP v3r5: Long-term added
Region | Data Provider | status as of today | target date MoP v3r5 implementation | notes
transparency platform | ENTSO-E | v3r4 | Q4 2025
Nordic CCR | Nordic RCC | v3r4 | 2026 | Nordic RCC is currently not providing the data to ENTSO-e TP. The plan is for the data to be published in the autumn of 2025 by them.

## TR 11.1.a offered capacity
Regulation article | Publication name
TR 11.1.a | offered capacity
Evolution: | MoP v3r4: Continuous allocations, offered capacity for intraday timeframe will be published separately per implicit allocation
country/area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r4
Albania | OST
Belgium | ELIA | v3r4 | DBS (XBID) reports the data for us.
Bosnia and Herzegovina | NOS BiH
Croatia | HOPS |  | DBS (XBID) reports the data for us.
Estonia | Elering
France | RTE | v3r4 | DBS (XBID) reports the data for us.
Germany | TenneT DE | v3r4 | DBS (XBID) reports the data for us.
Great Britain | Britned
Great Britain | RNP
Ireland | Eirgrid
Italy | Terna | v3r4 | JAO publishes the report
Kosovo | KOSTT
Lithuania | Litgrid
Montenegro | CGES
Netherlands | TenneT NL | v3r4
North Macedonia | MEPSO
Northern Ireland | SONI
Norway | Statnett | v3r3 | Q3 2026
Poland | PSE | v3r4
Portugal | REN
Romania | Transelectrica | v3r3 | TEL is not configured as Data Provider for implicit allocation. For explicit, we are using doc version 7:0. Later versions of MoP require version 7:3
Serbia | EMS
Slovakia | SEPS
Spain | REE | v3r4 | NTC-based capacity allocation
Sweden | Nord Pool Spot
Ukraine | Ukrenegro
Multiple | JAO
Multiple | DBS
Multiple | NOIS
Multiple | SEE CAO

## TR 12.1.d
Regulation article | Publication name
TR 12.1.d | Energy prices
Evolution: | MoP v3r4: Voluntary publication of intraday energy price
country/area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r4
Austria | APG |  | Not implemented. TSOs cannot decide upon implementation. NEMO (Nordpool/EPEX) needs to do this.
Belgium | ELIA | v3r3 | No view on ID implementation projects, since ELIA is neither Primary owner nor Data Provider of these data
Czechia | CEPS | v3r4
Estonia | ELERING
Germany | 50Hertz |  | Not implemented. German TSO cannot decide upon implementation. NEMO (EEX/EPEX) needs to do this.
Germany | AMPRION |  | Not implemented. German TSO cannot decide upon implementation. NEMO (EEX/EPEX) needs to do this.
Germany | TENNETDE |  | Not implemented. German TSO cannot decide upon implementation. NEMO (EEX/EPEX) needs to do this.
Germany | TRANSNETBW |  | Not implemented. German TSO cannot decide upon implementation. NEMO (EEX/EPEX) needs to do this.
Hungary | HUPX Ltd
Italy | TERNA
Latvia | AST | v3r3 | Not yet implemented. Current publication is done by NEMO.
Lithuania | LITGRID
Multiple | NORDPOOL
Netherlands | TENNETNL |  | Done by JAO for us
Poland | PSE | v3r4 | Intraday energy price to be not implemented.
Portugal | REN
Romania | TEL |  | ID not implemented (NEMOs need to decide)
Slovakia | SEPS
Spain | REE | v3r4 | To be implemented in sep-2025
Multiple | JAO
Multiple | NORDPOOL
Multiple | NUCS | v3r3
Multiple | STATNETT | v3r3 | Intraday prices publication not implemented

## TR 12.1.e
Regulation article | Publication name
TR 12.1.e | Implicit net positions
Evolution: | MoP v3r4: net positions convey implicit allocations only, total values published instead of intraday
country/area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r4
Austria | APG | v3r3 | v 3.4 Planned until end of 2025
Belgium | ELIA | v3r3 | Request for clarifications sent to ENTSOE
Czechia | CEPS | v3r4
Denmark | Statnett | v3r4
Estonia | ELERING
France | RTE |  | JAO reports the data for us.
Germany | 50Hertz | v3r4 | v3r4 implemented on CTA level. For publication on BZN level TP change is stil needed.
Germany | AMPRION | v3r4 | v3r4 implemented on CTA level
Germany | TENNETDE | v3r4 | v3r4 implemented on CTA level.
Germany | TRANSNETBW | v3r4 | v3r4 implemented on CTA level. For publication on BZN level TP change is stil needed.
Hungary | MAVIR | v3r4 | The IT development of ID data is underway. MAVIR will publish it, no later than Q2 2026
Italy | TERNA | v3r4 | Compliance to Mop v3r4 in Q3 2025
Latvia | AST | v3r3 | v3r4 implementation in near future.
Lithuania | LITGRID
Netherlands | TENNETNL |  | Done by JAO for us
Poland | PSE | v3r3
Portugal | REN
Romania | TEL | v3r4 | Configurations are done according to v3r4. The IT development is ongoing.
Slovakia | SEPS
Spain | REE | v3r4
Multiple | JAO
Multiple | NORDPOOL
Multiple | NUCS | v3r3
Multiple | STATNETT | v3r4 | Implemented

## TR 12.1.f
Regulation article | Publication name
TR 12.1.f | commercial schedules
Evolution: | MoP v3r4: TP will calculate and publish net positions per BZ
country/area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r3
Albania | OST
Austria | APG | v3r4
Belgium | ELIA | v3r5 | No changes detected at DP side since V3r3
Bosnia and Herzegovina | NOSBIH
Bulgaria | ESO | v3r3 | TP change still missing for v3r4 publication.
Croatia | HOPS
Czechia | CEPS | v3r3 | New version (7:3) will be upgraded along with MoP v3r5
Denmark | TENNETDE | v3r3
Estonia | ELERING
France | RTE | v3r3
Georgia | GSE
Germany | 50Hertz | v3r3 | TP change still missing for v3r4 publication.
Germany | AMPRION | v3r3 | TP change still missing for v3r4 publication.
Germany | TENNETDE | v3r4
Germany | TRANSNETBW | v3r3
Great Britain | BRITNED
Great Britain | ElecLink
Great Britain | RNP
Greece | ADMIE
Hungary | MAVIR | v3r4 | No changes detected compared to v3r4 content
Ireland | EIRGRID
Italy | TERNA | v3r4
Kosovo | KOSTT
Latvia | AST | v3r3
Lithuania | LITGRID
Moldova | MOLDELECTRICA
Montenegro | CGES
Netherlands | TENNETNL | v3r4
North Macedonia | MEPSO
Northern Ireland | SONI
Poland | PSE | v3r4 | Implementation on the TP side
Portugal | REN
Romania | TEL | v3r3 | We are using doc version 7:0. Later versions of MoP require version 7:3
Serbia | EMS
Slovakia | SEPS
Slovenia | ELES
Spain | REE | v3r4
Switzerland | SWISSGRID | v3r4 | NP feature existent in Data View for Swissgrid publications
Ukraine | UKRENERGO
Denmark | 50Hertz | v3r3
Multiple | NORDPOOL
Multiple | NUCS | v3r3
Multiple | STATNETT | v3r4 | Implemented

## TR 12.1.g
Regulation article | Publication name
TR 12.1.g | physical flows
Evolution: | MoP v3r4: For HVDC links, the published values refer to the sending end, unless specified otherwise in the explanatory text (some TSOs publish mid-point values).
country/area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r3
Albania | OST
Austria | APG | v3r4 | No relevance for APG
Belgium | ELIA | v3r3 | Explanatory note published on ETP GUI
Bosnia and Herzegovina | NOSBIH
Bulgaria | ESO | v3r3 | No HVDC links
Croatia | HOPS
Czechia | CEPS | v3r3
Denmark | 50Hertz | v3r3
Denmark | ENERGINET | v3r3
Denmark |  | v3r3
Estonia | ELERING
Finland | FINGRID | v3r3
France | RTE | v3r3
Georgia | GSE
Germany | 50Hertz | v3r3
Germany | AMPRION | v3r3
Germany | TENNETDE | v3r3 | For NordLink and Baltic Cable: The measured values at one side of the cable are published (Depending on the configured priorities and the direction of the load flow this leads to mixture of sending end and receiving end values being published)
Germany | TRANSNETBW | v3r3
Great Britain | ElecLink
Greece | ADMIE
Hungary | MAVIR | v3r3 | No changes detected compared to v3r4 content
Ireland | EIRGRID
Italy | TERNA | v3r3 | The measurements reported for HVDC interconnectors are recorded at the point of cable origin.
Kosovo | KOSTT
Latvia | AST | v3r3 | No HVDC links.
Lithuania | LITGRID
Moldavia | MOLDELECTRICA
Montenegro | CGES
Netherlands | TENNETNL | v3r4
North Macedonia | MEPSO
Northern Ireland | SONI
Norway | STATNETT | v3r3 | Will be implemented in Q2 2026
Poland | PSE | v3r4
Portugal | REN
Romania | TEL | v3r3 | No relevance for TEL, but we are using doc version 7:0. Later versions of MoP require version 7:3
Serbia | EMS
Slovakia | SEPS
Slovenia | ELES
Spain | REE | v3r4
Sweden | SVK
Switzerland | SWISSGRID | v3r4 | No operational HVDC links within or cross-border Swiss bidding zone
Ukraine | UKRENERGO
Note on C6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is TenneTs understanding correct that TP currently does not yet support to publish according to v3r4 (only v3r3)?

## TR 13.1.a
Regulation article | Publication name
TR 13.1.a | Redispatching
Evolution: | MoP v3r5: Added connecting TSO
country | TSO | status as of today | target date MoP v3r5 implementation | notes
transparency platform | ENTSO-E | v3r4
Austria | APG | v3r4 | Q1 2026 | No change for data provider
Belgium | Elia | v3r4 | Q2 2026
Croatia | HOPS |  | Q3-Q4 2026
Czechia | CEPS | v3r4 | Q1 2026
France | RTE
Germany | 50Hertz | v3r4 | Q4 2025 till Q1 2026
Germany | Amprion | v3r4 | Q4 2025 till Q1 2026
Germany | TenneT DE | v3r4 | Q4 2025 till Q1 2027
Germany | TransnetBW | v3r4 | Q4 2025 till Q1 2026
Hungary | MAVIR | v3r4 | Q2-Q3 2026
Ireland | Eirgrid
Netherlands | Tennet NL | v3r4
Northern Ireland | SONI
Norway | Statnett | v3r3 |  | This applies to Redispatching Cross Border, and we currently do not have this data.
Poland | PSE | v3r4 | Implementation date to be determined.
Serbia | EMS
Slovakia | SEPS
Slovenia | ELES
Sweden | SvK

## TR 13.1.b
Regulation article | Publication name
TR 13.1.b | Countertrading
Evolution: | MoP v3r5: Added connecting TSO
country | TSO | status as of today | target date MoP v3r5 implementation | notes
transparency platform | ENTSO-E | v3r4
Austria | APG | v3r4 | Q1 2026 | No change for data provider
Belgium | ELIA | v3r4 | Q2 2026
Croatia | HOPS |  | Q4 2026
Czechia | CEPS |  |  | N/E
Denmark | ENERGINET | v3r3 | 2026
Estonia | NORDPOOL
France | RTE | v3r4 | Q1 2026
Germany | 50Hertz
Germany | TENNETDE | v3r4 | Q1 2026
Germany | TRANSNETBW | v3r4 | Q4 2025 till Q1 2026
Great Britain | BRITNED
Great Britain | ELEXON
Italy | TERNA | v3r4 | Q4 2025
Latvia | AST |  |  | N/A, currenlty not used.
Lithuania | LITGRID
Northern Ireland | SONI
Norway | STATNETT | v3r4 | Q2 2026
Poland | PSE | v3r4 | Implementation date to be determined.
Portugal | REN
Slovakia | SEPS
Slovenia | ELES
Spain | REE | v3r4 | Q4 2025
Sweden | SVK | v3r4
Switzerland | SWISSGRID | v3r4 | Q1 2026

## TR 14.1.a
Regulation article | Publication name
TR 14.1.a | Aggregated installed generation capacity
Evolution: | MoP v3r4: Production type Energy Storage added. MoP v3r5: By default the 1MW threshold is not applicable. If a TSO applies the threshold of 1 MW, a disclaimer text should be put on the publication page.
country | TSO | status as of today | target date MoP v3r5 implementation | notes
transparency platform | ENTSO-E | v3r5
Albania | OST
Austria | APG | v3r3 | Q1 2026
Belgium | ELIA | v3r4 | Q2 2026 | Explanatory note will be published on ETP
Bosnia and Herzegovina | NOSBIH
Bulgaria | ESO | v3r4 | Q2 2026
Croatia | HOPS |  | Q1 2026 | If Energy Storage appears
Cyprus | TSOC | v3r3 | 2026
Czechia | CEPS | v3r4 | Q1 2026
Denmark | ENERGINET | v3r3 | 2026/2027
Estonia | ELERING
Finland | FINGRID | v3r3 | Q1 2026
France | RTE | v3r3 | Q2 2026
Georgia | GSE
Germany | 50Hertz | v3r5 | Change Implemented
Germany | AMPRION |  |  | publication done manually, via Web-GUI
Germany | TENNETDE | v3r5 | Both changes already implemented
Germany | TRANSNETBW | v3r5 | Change Implemented
Greece | ADMIE
Hungary | MAVIR | v3r3 | Q2-Q3 2026
Ireland | EIRGRID
Italy | TERNA | v3r5 | V3r5 Change Implemented | Production type Energy Storage will be added in Q1 2026 as the publication of the report is annual
Kosovo | KOSTT
Latvia | AST | v3r5 | Change Implemented | Currently no energy storage to report.
Lithuania | LITGRID | v3r5 | Q1 2026
Luxembourg | CREOS
Montenegro | CGES
Netherlands | TENNETNL | v3r3
North Macedonia | MEPSO
Northern Ireland | SONI
Norway | STATNETT | v3r3 | Q4 2026 | If any storage unit appear, we'll include them in the report. And we'd exclude the 1MW threshold
Poland | PSE | v3r3 | Q1 2026
Portugal | REN
Romania | TEL | v3r4 | Q1 2026
Serbia | EMS
Slovakia | SEPS
Slovenia | ELES
Spain | REE | v3r3 | Q1 2026
Sweden | SVK
Ukraine | UKRENERGO

## TR 14.1.b
Regulation article | Publication name
TR 14.1.b | Installed capacity per production unit
Evolution: | MoP v3r4: Production type Energy Storage added.
country | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
Albania | OST
Belgium | Elia | v3r5
Bosnia and Herzegovina | NOS BiH
Bulgaria | ESO | v3r3 | Q4 2026
Czechia | CEPS
Denmark | Energinet.dk | v3r3 | 2026/2027
Estonia | Elering
Finland | Fingrid | v3r3
France | RTE | v3r3 | Q2 2026
Georgia | GSE
Germany | 50Hertz | v3r5
Germany | Amprion |  | Data is coming from Master data directly
Germany | TenneT DE |  | Currently there are no publications regarding energy storage units from TenneT.
Great Britain | ELEXON
Greece | ADMIE
Hungary | MAVIR ZRt | v3r3 | Q2-Q3 2026
Ireland | EirGrid
Italy | Terna | v3r4 | Production type Energy Storage will be added in Q1 2026
Kosovo | KOSTT
Latvia | AST | v3r4 | Currently no energy storage units > 100 MW.
Lithuania | Litgrid | v3r4 | Q1 2026
Moldova | MOLDELECTRICA
Netherlands | TenneT NL | v3r3
North Macedonia | MEPSO
Northern Ireland | SONI
Norway | Statnett | v3r4 | No energy storage units with installed capacity > = 100 MW.
Poland | PSE | v3r4 | No energy storage units with installed capacity > = 100 MW.
Portugal | REN
Romania | Transelectrica | v3r4 | Energy storage is considered but publication duty exists only for units > 100 MW and such units are not yet in operation.
Serbia | EMS
Slovakia | SEPS
Slovenia | ELES
Spain | REE | v3r3 | Q1 2026
Sweden | SVENSKA KRAFTNÄT
Switzerland | swissgrid | v3r3 | Q2 2026
Ukraine | UKRENERGO
Multiple | EEX

## TR 15.1.a-d
Regulation article | Publication name
TR 15.1.a-d | unavailability of production and generation units
Evolution: | MoP v3r4: Production type Energy Storage added.
country | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
Albania | OST
Austria | APG |  | Data is published by EEX Transparency
Belgium | ELIA | v3r5
Bosnia and Herzegovina | NOSBIH
Bulgaria | ESO | v3r3
Croatia | HOPS |  | When Energy Storage units become operational, publication will depend on data owners, as they are usually < 100W
Czechia | CEPS | v3r3 | will be upgrade to 4.2 (under MoP v3r5 if XSD v 4.2 is available)
France | RTE | v3r3 | Q2 2026
Georgia | GSE
Germany | 50Hertz | v3r5
Germany | AMPRION | v3r3 | Not implemented, since publication duty exists only for units > 100 MW and such units are not yet in operation.
Germany | TENNETDE | v3r4 | Not implemented, since publication duty exists only for units >100 MW and such units are not yet in operation.
Germany | TRANSNETBW |  | Not implemented
Greece | ADMIE
Hungary | MAVIR | v3r3 | Q2-Q3 2026
Ireland | EIRGRID
Italy | TERNA | v3r4 | Production type Energy Storage will be added in Q1 2026
Kosovo | KOSTT
Latvia | AST |  | Provided by Nord Pool.
Lithuania | LITGRID
Montenegro | CGES
Multiple | EEX
Netherlands | TENNETNL | v3r3
North Macedonia | MEPSO
Northern Ireland | SONI
Poland | PSE | v3r4 | No energy storage units with installed capacity > = 100 MW.
Portugal | REN
Romania | TEL | v3r3 | Energy storage is considered, but publication duty exists only for units > 100 MW and such units are not yet in operation. We are using XSD version 3:0. MoP v3r5 requires version 4:2
Serbia | EMS
Slovakia | SEPS
Slovenia | ELES
Spain | REE | v3r3 | Q1 2026
Ukraine | UKRENERGO
Multiple | NORDPOOL
Multiple | NUCS | v3r3

## TR 16.1.a
Regulation article | Publication name
TR 16.1.a | actual generation per unit
Evolution: | MoP v3r4: Production type Energy Storage added.
country | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
Albania | OST
Belgium | ELIA | v3r5
Bosnia and Herzegovina | NOSBIH
Bulgaria | ESO | v3r3 | Implementation date to be determined.
Croatia | HOPS |  | When Energy Storage units become operational, publication will depend on data owners, as they are usually < 100W
Czechia | CEPS | v3r4
Denmark | ENERGINET | v3r3
Estonia | ELERING
Finland | FINGRID | v3r3
France | RTE | v3r3 | Q2 2026
Georgia | GSE
Germany | AMPRION | v3r3 | Not implemented, since publication duty exists only for units>100 MW and such units are not yet in operation.
Germany | TENNETDE | v3r4 | Not implemented, since publication duty exists only for units >100 MW and such units are not yet in operation.
Greece | ADMIE
Hungary | MAVIR | v3r3 | Q2 2026
Ireland | EIRGRID
Italy | TERNA | v3r4 | Change implemented
Kosovo | KOSTT
Latvia | AST | v3r4 | Currently no energy storage units > 100 MW.
Lithuania | LITGRID
Moldania | MOLDELECTRICA
Montenegro | CGES
Netherlands | TENNETNL | v3r3
North Macedonia | MEPSO
Northern Ireland | SONI
Norway | STATNETT | v3r4 | No energy storage units with installed capacity > = 100 MW.
Poland | PSE | v3r4 | No energy storage units with installed capacity > = 100 MW.
Portugal | REN
Romania | TEL | v3r4 | Energy storage is considered but publication duty exists only for units > 100 MW and such units are not yet in operation.
Serbia | EMS
Slovakia | SEPS
Slovenia | ELES
Spain | REE | v3r3 | Q1 2026
Spain | REE
Sweden | SVK
Ukraine | UKRENERGO
Multiple | EEX

## TR 16.1.b&c
Regulation article | Publication name
TR 16.1.b&c | aggregated generation per type
Evolution: | MoP v3r4: Production type Energy Storage added.
country | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
Austria | APG | v3r3 | Not implemented, energy storage units are not included yet.
Belgium | ELIA | v3r5
Bosnia and Herzegovina | NOSBIH
Bulgaria | ESO | v3r3 | Implementation date to be determined.
Croatia | HOPS |  | When Energy Storage units become operational, publication will be implemented
Cyprus | TSOC | v3r3
Czechia | CEPS | v3r4
Denmark | ENERGINET | v3r3
Estonia | ELERING
Finland | FINGRID | v3r3
France | RTE | v3r4
Georgia | GSE
Germany | 50Hertz | v3r4
Germany | AMPRION | v3r3 | Not implemented, energy storage units are not included yet.
Germany | TENNETDE | v3r4 | Not implemented yet; implementation is underway.
Germany | TRANSNETBW | v3r4
Greece | ADMIE
Hungary | MAVIR | v3r3 | Q2 2026
Ireland | EIRGRID
Italy | TERNA | v3r5
Kosovo | KOSTT
Latvia | AST | v3r3
Lithuania | LITGRID
Luxembourg | CREOS
Moldova | MOLDELECTRICA
Montenegro | CGES
Netherlands | TENNETNL | v3r3
North Macedonia | MEPSO
Northern Ireland | SONI
Norway | STATNETT | v3r4 | If any storage unit appear, we'll include them in the report.
Poland | PSE | v3r3 | Q1 2026
Portugal | REN
Romania | TEL | v3r4 | Storage included
Serbia | EMS
Slovakia | SEPS
Slovenia | ELES
Spain | REE | v3r3 | Q1 2026
Sweden | SVK
Switzerland | SWISSGRID | v3r4 | Not implemented, energy storage units are not included yet.
Ukraine | UKRENERGO

## TR 17.1.b&c
Regulation article | Publication name
TR 17.1.b&c | procured capacity and volumes
Evolution: | MoP v3r3: Merged TR 17.1.b and TR 17.1.c, adding allocation timestamp and type of product
country | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
Albania | OST
Austria | APG | v3r5
Belgium | ELIA | v3r5
Bosnia and Herzegovina | NOSBIH
Bulgaria | ESO | v3r2 | Merged TR 17.1.b and TR 17.1.c is under IT development.
Croatia | HOPS | v3r5 | Under IT development
Czechia | CEPS | v3r4
Denmark | ENERGINET
Denmark | ENERGINET | v3r3
Finland | FINGRID | v3r4
Finland | FINGRID
France | RTE | v3r5
Germany | 50Hertz | v3r5
Greece | ADMIE
Hungary | MAVIR | v3r4
Ireland | EIRGRID
Lithuania | LITGRID
Netherlands | TENNETNL | v3r4
Northern Ireland | SONI
Norway | STATNETT
Norway | STATNETT | v3r3 | Merged and we are using Balancing Market Document v4.4
Poland | PSE | v3r4 | Implementation date to be determined.
Portugal | REN
Romania | TEL | v3r3 | We are using XSD version 4:1. Later versions of MoP require version 4:4
Serbia | EMS
Slovakia | SEPS
Slovenia | ELES
Spain | REE | v3r4
Sweden | SVK
Sweden | SVK
Switzerland | SWISSGRID | v3r5
Ukraine | UKRENERGO
Multiple | BBCM
Multiple | NUCS | v3r3

## TR 17.1.f
Regulation article | Publication name
TR 17.1.f | balancing energy prices
Evolution: | ?
country | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
Albania | OST
Austria | APG | v3r4
Belgium | ELIA | v3r5 | We are using XSD version 4:4
Bosnia and Herzegovina | NOSBIH
Bulgaria | ESO | v3r3 | Under IT development. Currently is sent to TP IOP only
Croatia | HOPS | v3r5 | We are using XSD version 4:4
Czechia | CEPS | v3r3 | We may be on XSD version 4.1, which is the latest available documentation on the knowledge base. All MoPs from v3r3 on, requieres XSD version 4.4
Denmark | ENERGINET | v3r3
Estonia | ELERING
Finland | FINGRID | v3r4
France | RTE | v3r4
Germany | 50Hertz | v3r5
Germany | 50Hertz
Germany | TENNETDE | v3r4
Greece | ADMIE
Hungary | MAVIR | v3r4 | The MARI PICASSO platform will be complete in 2026 after joining.
Ireland (SEM) | EIRGRID
Ireland (SEM) | SONI
Italy | TERNA
Latvia | AST | v3r3
Lithuania | LITGRID
Montenegro | CGES
Netherlands | TENNETNL | v3r4
Norway | STATNETT | v3r4 | we are using Balancing Market Document v4.1
Poland | PSE
Portugal | REN
Romania | TEL | v3r3 | We are using XSD version 4:1. Later versions of MoP require version 4:4
Serbia | EMS
Slovakia | SEPS
Slovenia | ELES
Spain | REE | v3r4
Sweden | SVK
Switzerland | SWISSGRID
Ukraine | UKRENERGO
Multiple | LIBRA
Multiple | Mari
Multiple | NOIS
Multiple | NUCS
Multiple | TRANSNETBW | v3r4

## TR 17.1.g
Regulation article | Publication name
TR 17.1.g | imbalance prices
Evolution: | MoP v3r3: Aligned with imbalance pricing methodology; single or dual pricing and additional components
country | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
Albania | OST
Austria | APCS
Belgium | ELIA | v3r5 | We are using XSD version 4:4
Bosnia and Herzegovina | NOSBIH
Bulgaria | ESO | v3r3 | Under IT development. Currently is sent to TP IOP only
Croatia | HOPS |  | We are using XSD version 4:4
Czechia | CEPS | v3r5
Denmark | ENERGINET | v3r4
Estonia | ELERING
Finland | FINGRID | v3r4
France | RTE
Germany | 50Hertz | v3r5
Germany | TRANSNETBW | v3r4
Hungary | MAVIR | v3r4
Ireland | EIRGRID
Ireland (SEM) | SONI
Italy | TERNA | v3r5
Latvia | AST | v3r3
Montenegro | CGES
Netherlands | TENNETNL | v3r4
Poland | PSE
Portugal | REN
Romania | TEL | v3r4 | No changes detected for v3r5
Serbia | EMS
Slovakia | SEPS
Slovenia | ELES
Spain | REE | v3r4
Switzerland | SWISSGRID | v3r3 | Scarcity component to be added in 2026
Ukraine | UKRENERGO
Multiple | NUCS

## EB GL 12.3.k
Regulation article | Publication name
EB GL 12.3.k | description of algorithm
Evolution: | MoP v3r3: IN added MoP v3r5: FCR added
Process | Data Provider | status as of today | notes
transparency platform | ENTSO-E | v3r5
RR | Terre
mFRR | Mari
aFRR | Picasso | v3r3
FCR | FCR cooperation
IN | Picasso | v3r3

## EB GL 12.3.f
Regulation article | Publication name
EB GL 12.3.f | procured balancing capacity bids
Evolution: | MoP v3r3: Added allocation timestamp
country | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
Austria | APG | v3r5
Belgium | ELIA | v3r2 | v3r5 : Q2 2026
Czechia | CEPS | v3r4
Finland | FINGRID | v3r4
France | RTE | v3r5
Germany | 50Hertz | v3r5
Greece | ADMIE
Hungary | MAVIR | v3r5
Lithuania | LITGRID
Multiple | BBCM
Multiple | NUCS | v3r3
Netherlandds | TENNETNL | v3r4
Poland | PSE | v3r2 | Implementation date to be determined.
Portugal | REN
Romania | TEL | v3r4 | No changes detected for v3r5
Slovakia | SEPS
Spain | REE | v3r4
Switzerland | SWISSGRID | v3r5

## IFs elastic demands
Regulation article | Publication name
mFRR IF art. 3.4 aFRR IF art. 3.4 | Elastic demands
Evolution: | MoP v3r5: Added aFRR
process | Party | status as of today | target date MoP v3r5 implementation | notes
transparency platform | ENTSO-E | v3r4
mFRR | Mari
aFRR | Picasso |  |  | will be implemented in 2025. Data is currently published on the TransnetBW website

## SO GL 185.4
Regulation article | Publication name
SO GL 185.4 | Results of the criteria application process
Evolution: | MoP v3r3: PDF replaced by structured data MoP v3r4: Negative values permitted for mean and percentiles of the FRCE
area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
Greece | ADMIE
LFC block Germany | AMPRION | v3r3
SNA Continental Europe | AMPRION | v3r3
Austria | APG | v3r5
Czechia | CEPS | v3r5
Slovenia | ELES
Belgium | ELIA | v3r5
Poland | PSE | v3r4
Spain | REE | v3r4
France | RTE | v3r5
Switzerland | SWISSGRID | v3r5
Italy | TERNA | v3r5
Bulgaria | ESO | v3r4

## SO GL 186.2
Regulation article | Publication name
SO GL 186.2 | imbalance netting process
Evolution: | MoP v3r3: PDF replaced by structured data
area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
SNA CE | AMPRION |  | no XML Format defined, only PDF
SNA CE | SWISSGRID |  | no XML Format defined, only PDF
SNA CE | REE
SNA CE | ADMIE

## SO GL 187.2
Regulation article | Publication name
SO GL 187.2 | FCR amount and shares
Evolution: | MoP v3r3: Structure of data revised
area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
Continental Europe | AMPRION | v3r3
Nordic | SVK
Germany (DE_DK1_LU) | AMPRION | v3r3
Austria | APG | v3r5
Czechia | CEPS | v3r5
Slovenia (SI_HR_BA) | ELES
Belgium | ELIA | v3r5
France | RTE | v3r5
Switzerland | SWISSGRID | v3r5

## SO GL 188.3
Regulation article | Publication name
SO GL 188.3 | FRR capacity forecast
Evolution: | MoP v3r3: PDF replaced by structured data
area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
Germany (DE_DK1_LU) | AMPRION | v3r3
Austria | APG | v3r5
Czechia | CEPS | v3r5
Belgium | ELIA | v3r5
Bulgaria | ESO | v3r5
Poland | PSE | v3r3
Spain | REE | v3r5
France | RTE | v3r5
Italy | TERNA | v3r5
LFB¦HU | MAVIR |  | MAVIR has only been able to publish FRR actual capacity (legacy) so far. The new format is under IT development.

## SO GL 188.4
Regulation article | Publication name
SO GL 188.4 | FRR actual capacity
Evolution: | MoP v3r3: Structure of data revised
area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
DE_DK1_LU | AMPRION | v3r3
LFB¦BE | ELIA | v3r5
LFB¦HU | MAVIR |  | MAVIR has only been able to publish FRR actual capacity (legacy) so far. The new format is under IT development.
LFB¦PL | PSE | v3r3
Austria (AT) | APG | v3r3
Czech Republic (CZ) | CEPS | v3r5
Spain (ES) | REE | v3r5
France (FR) | RTE | v3r5
Switzerland (CH) | SWISSGRID | v3r5
Italy (IT) | TERNA | v3r5 | Change Implemented

## SO GL 189.2
Regulation article | Publication name
SO GL 189.2 | RR capacity forecast
Evolution: | MoP v3r3: PDF replaced by structured data
area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
DE_DK1_LU | AMPRION |  | Amprion is not data provider for RR
Austria | APG |  | No RR in APG
Czech Republic | CEPS | v3r5
Belgium | ELIA |  | Publication not implemented, as RR not aplicable for TSO ELIA
Bulgaria | ESO |  | No RR in ESO
Poland | PSE | v3r3
Spain | REE | v3r5
France | RTE | v3r5
Italy | TERNA | v3r5
LFB¦HU | MAVIR |  | MAVIR system does not contain SO GL 189.3 RR Actual Capacity. We do not publish RR type.

## SO GL 189.3
Regulation article | Publication name
SO GL 189.3 | RR actual capacity
Evolution: | MoP v3r3: Structure of data revised
area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
DE_DK1_LU | AMPRION |  | Amprion is not data provider for RR
LFB¦BE | ELIA |  | Publication not implemented, as RR not aplicable for TSO ELIA
LFB¦HU | MAVIR |  | MAVIR system does not contain SO GL 189.3 RR Actual Capacity. We do not publish RR type.
LFB¦PL | PSE | v3r3
Austria (AT) | APG |  | No RR in APG
Czech Republic (CZ) | CEPS | v3r5 | CEPS is not data provider
Spain (ES) | REE | v3r5
France (FR) | RTE | v3r5
Switzerland (CH) | SWISSGRID |  | RR products deprecated starting 2026
Italy (IT) | TERNA | v3r5

## SO GL 190.1
Regulation article | Publication name |  |  | No DP configured
SO GL 190.1 | Sharing of RR and FRR
Evolution: | MoP v3r3: Structure of data revised
area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
LFC block France |  |  | France is not concerned by sharing of RR and FRR.
LFC block Germany

## SO GL 190.2
Regulation article | Publication name
SO GL 190.2 | Sharing of FCR
Evolution: | MoP v3r3: PDF replaced by structured data
area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
Switzerland | Swissgrid | v3r2 | Previously been Data Provider only for legacy data item
Czechia | CEPS |  | Our TSO is not a data provider for this data set
Spain | REE
Greece | ADMIE
Croatia | HOPS
Slovenia | ELES
SNA Continental Europe | Swissgrid

## SO GL 190.3
Regulation article | Publication name
SO GL 190.3 | Exchanged reserve capacity
Evolution: | MoP v3r3: PDF replaced by structured data
area | TSO | status as of today | notes
transparency platform | ENTSO-E | v3r5
DE_DK1_LU | AMPRION | v3r3
Austria | AMPRION | v3r3
Austria | APG | v3r3
Czech Republic | CEPS | v3r5
Belgium | ELIA | v3r5
Austria | APG

## DC links
Regulation article | Publication name
n/a | DC links
Evolution: | MoP v3r4: Publication of DC links with their loss factors
Region | Data Provider | status as of today | target date MoP v3r5 implementation
transparency platform | ENTSO-E | v3r3

## references
MoP | reporting cut-off date | next milestone
v3r2 | status as of today | target date MoP v3r5 implementation
v3r3
v3r4
v3r5